## Estimation
Milestone 1 |  |  |  | Timeline (Days) | Payment | Payment | Comment
Module Name | Sub Module | Tasks | Hours |  |  | 50%
Requirement Analysis & Project Management | Requirement Analysis & Project Management | Requirement analysis and study project related documents. | 6
Listing requirements
Preparing Project Plan, task list, assignment of tasks, explanation to developers
Database | Database Design | Database Design | 6
Design | Layout |  | 4
Milestone 2 |  |  |  | Timeline (Days) | Payment | Payment | Comment
Admin Section | User Login | User Login Screen | 4 |  |  | 25%
| Admin Dashboard | Edit My Profile(Name, Email, Phone etc.) | 3
|  | Change Password | 2
| Chemist/Pharmacy | Add/Edit Pharmacy | 3
|  | Add/Edit Sub Users to Pharamcy/Chemist | 3
|  | View/Delete/Enable/Disable/Search Pharmacy | 4
| Supplier | Add/Edit Supplier | 2
|  | Add/Edit Sub Users to Supplier | 2
|  | View/Delete/Enable/Disable/Search Suppliers | 3
| Purchase Order | Search Purcahse Orders | 4
View Purcahse Orders
View Purcahse Order Details
| Admin Users | Add/Edit Admin Users | 5
View/Delete/Enable/Disable admin users
Chemist/Pharmacy | Pharmacy Dashboard | Alerts/Notifications | 3
|  | Edit My Profile(Name, Email, Phone etc.) | 1
|  | Change Password | 1
| Supplier | View/Delete/Enable/Disable Suppliers | 2
|  | Add New Supplier | 1
|  | Approve Supplier | 1
| Purchase Order | Create New Purchase Order | 5
|  | View/Search Purcahse Orders | 3
|  | View/Download Purcahse Order Details | 1
|  | Edit/Approve Purcahse Order | 2
|  | Pdf generation of purcahse order | 4
|  | Email Notification to suppliers | 3
| Manage Users | Add/Edit Users | 4
View/Delete/Enable/Disable/Search Users
| Item Master | Add/Edit Item | 3
View/Delete Items
Supplier Section | Supplier Dashboard | Alerts/Notifications | 3
|  | Edit My Profile(Name, Email, Phone etc.) | 1
|  | Change Password | 1
| Chemist | View/Delete/Enable/Disable Chemists | 2
|  | Add New Chemists | 1
|  | Approve Chemists | 1
| Purchase Order | View/Search Purcahse Orders | 2
|  | View/Download Purcahse Order Details | 1
|  | Forward Purchase Order | 2
|  | Change Status of purcahse order | 1
| Manage Users | Add/Edit Users | 4
View/Delete/Enable/Disable/Search Users
[6 empty] | Payment | Comment
System Testing | Module Testing |  | 12 |  |  | 25%
Integration Testing
System Testing
Deployment
Miscellaneous
Total Hours |  |  | 116
Technology:
Programming language: | C# .NET + MVC | Development service charge: xxx USD
Payment Mode: Wire transfer or PayPal
Payment Terms: Mentioned in Proposal
Database: | SQL Server | Warranty: 60 days for free bug fixing.