## Estimation
Hours
Requirement Analysis & Project Management |  |  |  | 64 | Timeline (Days) | Payment | Comment
Module Name | Sub Module | Tasks | Web
Requirement Analysis & Project Management | Requirement Analysis & Project Management | Requirement analysis and study the given reference site(https://www.opendining.net), project related documents. | 24
Listing requirements
Preparing Project Plan, task list, assignment of tasks, explanation to developers
Database | Database Design and creation | Database Design - Tables | 24
Design | Layout |  | 16
Admin Section |  |  |  | 600 | Timeline (Days) | Payment | Comment
System Admin | Admin Login |  | 4
| Admin Dashboard |  | 16
Master sesction | Mange Countries |  | 5
| Manage Banners |  | 5
| Mange Categories |  | 6
| Manage Supplier |  | 6
| Manage Product |  | 14 |  |  |  | We consider photo, description, name etc. We will provide a section where system admin can add features using lable and values which in turn render on front side. We show images zoom mode on front side as other site does (Flipkart)
| Recurring Profile | [5 empty] | Need more detail
| Mange Filters | [5 empty] | Need more detail
| Manage Attributes | [5 empty] | Need more detail
| Mange Options | [5 empty] | Need more detail
| Mange Manufactures |  | 8
| Manage Downloads | [5 empty] | Need more detail
| Manage Reviews | [5 empty] | Need more detail
| Manage Information | [5 empty] | Need more detail
| Product Catalogues |  | 12
Extension - Add Ons | Installer | [5 empty] | Need more detail
| Modifications | [5 empty] | Need more detail
| Modules | [5 empty] | Need more detail
| Shipping |  | 14 |  |  |  | Consideration: supplier will get notification and system admin will do updation in system for delivery and payment
| Payment | [5 empty] | Need more detail
| Order Totals | [5 empty] | What is Order Total here?
| Feeds | [5 empty] | Need more detail
| Anti-Fraud | [5 empty] | Need more detail
Cart | Manage Order |  | 12
| Recurring Order |  | 12 |  |  |  | Consideration: Complete order will be reoccur with same detail. OR provide more detail.
| Mange Returns of Order |  | 12
| Mange Voucher |  | 12
| Paypal Settings |  | 8
| Mange Customers (Store owner) |  | 8
| Mange Buyers |  | 8
Tools | Uploads | [5 empty] | Need more detail
| Backup/Restore | [5 empty] | Need more detail
| text_export_import | [5 empty] | Need more detail
| Error Log |  | 4
| Import Catalogues |  | 6
Reports | Sales |  | 20 |  |  |  | Consideration: 3 reports for each type i.e Sales, Product etc.
| Products |  | 20
| Customers |  | 20
| Marketing |  | 20
| Transactions |  | 20
Sharing (Promotion) | Marketing |  | 12
| Affiliates | [5 empty] | Need more detail
| Coupons |  | 16 |  |  |  | Consideration: Coupon management which will be used in front side
| Mail |  | 8 |  |  |  | Consideration: 3 different mails for promotion sent using service
Settings | System Settings |  | 12
| Design | [5 empty] | Need more detail
| Users |  | 8
| Localisation | [5 empty] | Consideration: we do not consider localization.
Buyer page |  |  |  | 244 | Timeline (Days) | Payment | Comment
Public Front side - Buyer | Main Page of Website |  | 42
| Buyer Login |  | 4
| Changes Password |  | 4
| Manage Profile |  | 4
| Order History |  | 12
| Reward Points |  | 12
| Place Order |  | 42
| Product Return |  | 12
| Track Order |  | 8
| Address book |  | 8
| Share points to others |  | 8
| Cancel Order |  | 8
| Search Products |  | 8
| Product detail page |  | 8
| History management |  | 12
| Product Review and Star |  | 8
| Recommaded Product to other emploee |  | 8
| Share Product on FB |  | 8
| Alert and Notification |  | 12
| Dashboard |  | 16
Customer Login |  |  |  | 62 | Timeline (Days) | Payment | Comment
Customer Login | Customer Login |  | 4
| Manage Users |  | 6
| Role Rights |  | 4
| Manage SubGroup for Grouping |  | 8
| Purchase points |  | 8
| Dashboard |  | 16
| Reports |  | 16
Add On Features |  |  |  | 42 | Timeline (Days) | Payment | Resource Details
Other add on | Chat Integration | Between Front Page User + System Admin | 10 |  |  |  | Consideration Third party chat integration
| Template layout | [5 empty] | we write a code in such a way that code can be reusable for any template, currently focus on one template and we do estimate efforts for other theme later on.
| FAQ |  | 16
| Customer Card |  | 16
| Gamification | [5 empty] | Need more detail
| Supplier Login | [5 empty] | Need more detail
Milestone 7 |  |  |  |  | Timeline (Days) | Payment | Resource Details
System Testing | Resolutions + Browsers + Responsive Considerations(as mention per section) | Win OS - FF, Chrome, Microsoft Edge | 95
Module Testing
Integration Testing
System Testing
| Miscellaneous | client communication, project analysis and queries, mid demos to client, final uploading to client’s server and final testing on client’s server
Total Hours |  |  | 948 | 948
Development service charge: xxx USD
Payment Mode: Wire transfer or PayPal
Payment Terms: Mentioned in Proposal
Warranty: 60 days for free bug fixing.
Technology:
Programming language: | asp.NET MVC, WebAPI, Javascript, Angular JS
Database: | SQL Server